## Slide 1: AI Champions Program Progress Update
Discussion document
September 2026

## Slide 2: Agenda
Progress update
AI engine and core data platform
AI-based unified BoQ
Capex estimation solution
Next steps

## Slide 3: Recap: 3 solutions in one connected workflow on a single AI platform
FOUNDATIONS
SINGLE PRE AI PLATFORM FOR ALL IN-HOUSE SOLUTIONS
Concept design
Project brief
Technical design
CAPEX estimation
Estimate project cost in different detail levels using historical data and item-level price forecasting model
Today’s agenda
Construction
Construction control tower
Monitor progress and budget in one view
Tender
Tender bid evaluation
Compare bids on unified BoQ with AI-suggested prices and flags
To start in Oct-26
Agentic workflow design
PRE AI stack
PRE core data platform
AI-based unified BoQ
Today’s agenda
Ongoing
Ongoing
Today’s agenda

## Slide 4: AI Champions Program Action Plan
Solutions
PRE core
data platform
PRE AI stack
Tender bid evaluation
CAPEX estimation
AI-based unified BoQ
Construction control tower
Agentic workflow design
Current focus
Not started
Key highlights
Completed
1
2
3
1
2
3
Jul
Aug
Sep
Target state agentic workflow design
MEP PoC
Scale-up to all categories
BoQ maintenance solution
PRE central database creation for all BoQs, bids and contracts
PRE data lake setup
COINS & Aconex integration (TBD on technical feasibility)
Scale to all categories
MEP PoC
MVP agentic workflow
AI stack cloud environment
Long-term architecture design
PoC
Agentic workflow
Scale-up to all projects
Analytics control tower design
SPRINT 1
Oct
Nov
SPRINT 2
Dec
Foun-dations
Jan
SPRINT 3
Continuous support to AI Transformation Team on deployment
TODAY
Application development on cloud server
  Project brief and technical design designs completed
  Crescent Office L35-36 MEP tender is run for BoQ unification and CAPEX estimation
  MEP unified BoQ review completed by teams
  BoQ unification expanded beyond MEP to cover all categories – will start team reviews in October
  Historical data collection and processing completed
  Application development effort started on Azure cloud
  COINS and Aconex integration discussions ongoing with vendors

## Slide 5: Agenda
Progress update
AI engine and core data platform
AI-based unified BoQ
Capex estimation solution
Next steps

## Slide 6: We developed an integrated set of AI agents to extract/clean data, create unified BoQ codes and CAPEX estimation
Flags BoQ files across thousands of folders for targeted processing
Evaluates each Excel cell and layout to prepare unique plan for each file to extract/clean data
Data Extraction and Cleaning
BoQ Unification
CAPEX Estimation
Identifes and generates physical parts under WBS and map BoQ items to them
Domain-specific trained agents generate specs, and main specs are selected for unification based on team review and spec dominance
Top – down winner inflation: Select winner bids, estimates CAPEX adjusting inflation
Bottom – up costing: Generates cost structure with deep research and forecasts key drivers (e.g. material, energy) weighted by each driver’s share
processed Excel sheets
14K
extracted BoQ lines
1.6Mn
parsed physical parts
+1K
generated specs
7.5K
selected main specs for unification
3K

## Slide 7: 284 out of 353 (80%) procurement packages since 2023 are captured with item-level prices
50
Has prices but no winner
(work-in-progress)
59
Material / labor cost not split
65
BoQ captured but limited package mapping
316
Packages with available item data
284
BoQs with prices
169
Packages with identified winner
174
BoQs with data quality issues
32
Packages with no available price
37
Package with no available BoQ
49
Ongoing procurement
Data gaps
Perfect data
Total scope
The current data set volume and quality are sufficient enough to run AI solutions
90% of total packages
80% of total packages
45% of total packages
Good data
353
Awarded procurement packages
Total scope

## Slide 8: Agenda
Progress update
AI engine and core data platform
AI-based unified BoQ
Capex estimation solution
Next steps

## Slide 9: 2. Switch to the BoQ search and library

## Slide 10: Agenda
Progress update
AI engine and core data platform
AI-based unified BoQ
Capex estimation solution
Next steps

## Slide 11: 3. Switch to the project brief report and technical design view

## Slide 12: We aim to integrate with COINS and Aconex for seamless agentic flow but couldn not achieve it yet
1. COINS
Need it for IPCs to track CAPEX actualization and budget tracking
OPTIONS TO INTEGRATE
Next step: Final feasibility discussions ongoing with COINS side to make a decision
2. Aconex
OPTIONS TO INTEGRATE
Need it for procurement bids to run bid evaluation and identify winner prices
  Option 1: Buy COINS Analytics solution license
    $15k per year + $16k one-time fee
  Option 2: Build an in-house integration to get read-only access
    Technical discussions ongoing with COINS (the vendor does not want to allow it)
  Option 1: Build API integration
  Option 2: Get direct database access
STATUS
  Ticket opened to Oracle
  Technical support assigned
Next step: Confirm with Oracle technician the feasibility of options

## Slide 13: Agenda
Progress update
AI engine and core data platform
AI-based unified BoQ
Capex estimation solution
Next steps

## Slide 14: Delivery targets until end of September
Solutions
PRE core
data platform
PRE AI stack
Tender bid evaluation
CAPEX estimation
AI-based unified BoQ
Construction control tower
Agentic workflow design
Current focus
Not started
Next steps
Completed
Jul
Aug
Sep
Target state agentic workflow design
MEP PoC
Scale-up to all categories
BoQ maintenance solution
PRE central database creation for all BoQs, bids and contracts
PRE data lake setup
COINS & Aconex integration (TBD on technical feasibility)
Scale to all categories
MEP PoC
MVP agentic workflow
AI stack cloud environment
Long-term architecture design
PoC
Agentic workflow
Scale-up to all projects
Analytics control tower design
SPRINT 1
Oct
Nov
SPRINT 2
Dec
Foun-dations
Jan
SPRINT 3
Continuous support to AI Transformation Team on deployment
TODAY
Application development on cloud server
  1. Release first MVP to users:
  BoQ Search Engine
  Technical Design View for MEP packages
  3. Finalize concept design, procurement and construction interfaces for CAPEX estimation
  2. Start end-user unified BoQ review for non-MEP categories